## Sheet1
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME
Guillem	scrollable empty / Background.	4h	6h
Santiago	Module Audio: Music and sound effects	2h	2h 30min
Guillem	Included NeoGeo screen, Welcome screen, Haohmaru's stage(animated) and Celebration screen with swi	2h	3h 45min
Santiago	correct soundtrack for each scene	20min	10min
Guillem	Version 0.3: Move player without collisions
Òscar	Animate player when moving
	Shoot a particle
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME
	FadeToBlack when screen switching added
Santiago	FX of the particle	10min	15 min
Guillem	Version 0.4: Camera limits	10min	3h
Guillem	colliders for player and particles	5h	6h
	Player has to collide with something
Guillem	God Mode	15min	4min
	Version 0.5:
Santiago	All sound effects implemented in wav format	20 min	20 min
Guillem	direct win/lose
	mechanics: sword slash
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME