## Sheet1
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME
Guillem	Version 0.1: scrollable empty / Background.
Santiago	Module Audio: Music and sound effects	1h	2h 30min
Guillem	Version 0.2: Screen switching (Welcome screen, character selection,
Santiago	correct soundtrack for each scene	20min	10min
Òscar	Version 0.3: Move player without collisions	30 min	20 min
Òscar	Animate player when moving	1h	1h 30 min
Òscar	Shoot a particle
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME
Santiago	FX of the paticle	10min	15 min
	Version 0.4: Camera limits
	colliders for player and particles
	Player has to collide with something
Guillem	God Mode	15min	4min
	Version 0.5:
Santiago	All sound effects implemented in wav format
	direct win/lose
	mechanics: sword slash
	Minimum UI