## Sheet1
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME	DATE
Guillem	scrollable empty / Background.	4h	6h	20/04/18
Santiago	Module Audio: Music and sound effects	2h	2h 30min	20/04/18
Guillem	Included NeoGeo screen, Welcome screen, Haohmaru's stage(animated) and Celebration screen with swi	2h	3h 45min	20/04/18
Santiago	correct soundtrack for each scene	20min	10min	21/04/18
Guillem	Version 0.3: Move player without collisions	30 min	45 min	201/04/2018
Òscar	Animate player when moving	40 min	2h	22/04/18
Òscar/Guillem	Shoot a particle	1h	4h	22/04/18
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME	DATE
Òscar	FadeToBlack when screen switching added	15min	20min	22/04/18
Santiago	FX of the particle	10min	15 min	23/04/18
Guillem	Version 0.4: Camera limits	10min	3h	23/04/18
Guillem	colliders for player and particles	5h	6h	25/04/18
Guillem	Player has to collide with something	1h	8h	25/04/18
Guillem	God Mode	15min	4min	25/04/18
Guillem	F1 debug tool added (show colliders)	5min	5min	25/04/18
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME	DATE
Santiago	All sound effects implemented in wav format	20 min	20 min	26/04/18
Guillem	direct win/lose	10min	15min	26/04/18
Òscar	mechanics: sword slash	1h	3h	26/04/18
Òscar/ Santiago	All new animations: Jump Forward/Backward- Crouch up/down	1h	5h	26/04/18
Guillem/Marc	HP bars	3h	7h	27/04/18
Guillem/Òscar	state input manager	5h	14h	27/04/18
Marc	Bug Fixes	2h	3h	28/04/18
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME	DATE
Òscar	Animation bugs fixes	3h	2h 30min	28/04/18
Santiago	Auidio bug fixes	2h	2h	28/04/18

TOTAL TIME		35h	74h 30min