## Sheet1
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME
Guillem	scrollable empty / Background.	4h	6h
Santiago	Module Audio: Music and sound effects	2h	2h 30min
Guillem	Included NeoGeo screen, Welcome screen, Haohmaru's stage(animated) and Celebration screen with swi	2h	3h 45min
Santiago	correct soundtrack for each scene	20min	10min
Guillem	Version 0.3: Move player without collisions	30 min	45 min
Òscar	Animate player when moving	40 min	2h
Òscar/Guillem	Shoot a particle	1h	4h
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME
Òscar	FadeToBlack when screen switching added	15min	20min
Santiago	FX of the particle	10min	15 min
Guillem	Version 0.4: Camera limits	10min	3h
Guillem	colliders for player and particles	5h	6h
Guillem	Player has to collide with something	1h	8h
Guillem	God Mode	15min	4min
Guillem	F1 debug tool added (show colliders)	5min	5min
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME
Santiago	All sound effects implemented in wav format	20 min	20 min
Guillem	direct win/lose	10min	15min
Òscar	mechanics: sword slash	1h	3h
Òscar/ Santiago	All new animations: Jump Forward/Backward / - Crouch up/down	1h	5h
Guillem/Marc	HP bars	3h	7h
Guillem/Òscar	state input manager	5h	14h
Marc	Bug Fixes	2h	3h
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME
Òscar	Animation bugs fixes	3h	2h 30min
Santiago	Auidio bug fixes	2h	2h