## Sheet1
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME
Guillem	Version 0.1: scrollable empty / Background.	4h	6h
Santiago	Module Audio: Music and sound effects	2h	2h 30min
Guillem	Version 0.2: Screen switching (Welcome screen, character selection,	2h	3h 45min
Santiago	correct soundtrack for each scene	20min	10min
Guillem	Version 0.3: Move player without collisions
Òscar	Animate player when moving
	Shoot a particle
GROUP MEMBER	TASK	ESTIMATED TIME	ACTUAL TIME
Santiago	FX of the particle	10min	15 min
Guillem	Version 0.4: Camera limits	10min	3h
Guillem	colliders for player and particles	5h	6h
	Player has to collide with something
Guillem	God Mode	15min	4min
	Version 0.5:
Santiago	All sound effects implemented in wav format
	direct win/lose
	mechanics: sword slash
	Minimum UI